## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Manually Scheduled | System Planning | 21 days | January 23, 2017 8:00 AM | February 20, 2017 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Introduction to System Analysis and Design | 7 days | January 23, 2017 8:00 AM | January 31, 2017 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Analyxing the Business Case | 7 days | February 1, 2017 8:00 AM | February 9, 2017 5:00 PM | 2 | 2
4 | Yes | Auto Scheduled | Managing Systems Projects | 7 days | February 10, 2017 8:00 AM | February 20, 2017 5:00 PM | 3 | 2
5 | Yes | Auto Scheduled | Systems Analysis and Design | 42 days | February 21, 2017 8:00 AM | April 19, 2017 5:00 PM | 1 | 1
6 | Yes | Auto Scheduled | Requirements Modeling | 7 days | February 21, 2017 8:00 AM | March 1, 2017 5:00 PM |  | 2
7 | Yes | Auto Scheduled | Data and Process Modeling | 7 days | March 2, 2017 8:00 AM | March 10, 2017 5:00 PM | 6 | 2
8 | Yes | Auto Scheduled | Development Strategies | 7 days | March 13, 2017 8:00 AM | March 21, 2017 5:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Output and User Interface Design | 7 days | March 22, 2017 8:00 AM | March 30, 2017 5:00 PM | 8 | 2
10 | Yes | Auto Scheduled | Data Design | 7 days | March 31, 2017 8:00 AM | April 10, 2017 5:00 PM | 9 | 2
11 | Yes | Auto Scheduled | System Architecture | 7 days | April 11, 2017 8:00 AM | April 19, 2017 5:00 PM | 10 | 2
12 | Yes | Auto Scheduled | Systems Implementation and Maintenance | 14 days | April 20, 2017 8:00 AM | May 9, 2017 5:00 PM | 5 | 1
13 | Yes | Auto Scheduled | Managing Systems Implementation | 7 days | April 20, 2017 8:00 AM | April 28, 2017 5:00 PM |  | 2
14 | Yes | Auto Scheduled | Managing System Security | 7 days | May 1, 2017 8:00 AM | May 9, 2017 5:00 PM | 13 | 2
15 | Yes | Manually Scheduled | Final Exam | 1 day | May 15, 2017 8:00 AM | May 15, 2017 5:00 PM | 14 | 1